## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 448 | 1.Choose the data either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning(like removing unnecessary text like emojis) and Normalization (like lowercasing, tokenizing, lemmatizing , POS tagging) 5.Using multiprocessing techniques, find the word and its counts. | MUST HAVE |  |  | 3- Completed
2 | 2 | 448 | 1.Sentiment analysis / Text Classification / Topic modeling 2.Store in DB 3.Apply parallelism 4.Send the summary email | MUST HAVE |  |  | 3- Completed
3 | 3 | 448 | 1.Load Dataset. 2.Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3.Saves results into a CSV (or your text storage DB). 4. Mail the csv file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | MUST HAVE |  |  | 3- Completed
4 | 4 | 448 | Create an UI part for your project.(preferably using streamlit) | MUST HAVE |  |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task start date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 1 | 1.Choose the data either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning(like removing unnecessary text like emojis) and Normalization (like lowercasing, tokenizing, lemmatizing , POS tagging) 5.Using multiprocessing techniques, find the word and its counts. | 2025-09-09 | 2025-09-18 |  | Coding | completed | 8hrs
448 | 2 | 1.Sentiment analysis / Text Classification / Topic modeling. 2.Store in DB 3.Apply parallelism 4.Send the summary email | 2025-09-24 | 2025-09-04 |  | Coding | completed | 8hrs
448 | 3 | 1.Load Dataset. 2.Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3.Saves results into a CSV (or your text storage DB). 4. Mail the csv file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | 2025-10-10 | 2025-10-17 |  | Coding | completed | 10hrs
448 | 4 | Create an UI part for your project using streamlit | 2025-10-18 | 2025-10-25 |  | Coding | completed | 10hrs
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-09-09 | MULTIPROCESSING | Multiprocessing completed
1 | 2025-10-09 | sqlite3 database importing | imported the sqlite3 databse
1 | 15-9-25 | Data exploration(choose the data ) | choosen small text and explored the data
1 | 18-9-25 | presentation | milestone -1 presentation completed
2 | 24-9-25 | email alert | completed to send email summary
2 | 26-9-25 | vectorizer | completed to find countvectorizer and tfidf vectorizer
2 | 30-9-25 | final process for milestone one | implemented topic modeling and stored the data in db and performed parallelism and sent summary mail
2 | 2025-03-10 | presentation | presented the work
2 | 2025-04-09 | upload to drive | uploaded to drive link
3 | 2025-11-10 | Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. | performed unsupervised algorithm for topic modeling
3 | 13/10/25 | Saves results into a CSV (or your text storage DB). | saved the results to the csv file
3 | 14/10/25 | Mail the csv file | mailed the results using csv file
3 | 15/10/25 | 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | measured the performance of the algorithms lda and nmf using topic modeling
3 | 16/10/25 | presentation | presented the work
3 | 17/10/25 | upload to drive | submitted the work through drive
4 | 18/10/25 | Create an UI part for your project.(preferably using streamlit) | Started working on streamlit application
4 | 25/10/25 | presentation | presented the work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-09 | 18-9-25 | SAIPRIYA | cleaned and normalized the data | completed tasks for milestone 1 | no
2 | 2 | 24/9/25 | 2025-04-09 | SAIPRIYA | implemented the topic modeling and sent summary mail | completed tasks for milestone 2 | no
3 | 3 | 2025-10-10 | 17/9/25 | SAIPRIYA | performed unsupervised algorithm using topic mdeling and measured time performance between lda and nmf | completed tasks for milestone 3 | no
4 | 4 | 18/9/2025 | 25/9/25 | SAIPRIYA | created ui part for the project | completed tasks for milestone 4 | no
5
6
7